## Slide 1
RISC-V DUAL-CORE SoC
Coherent Memory Subsystem — Verified Engineering Status
A data-grounded review: every figure in this deck is sourced directly from
OpenLane/LibreLane metrics, STA reports, and RTL/testbench source — not from
prior narrative claims.
September 2026

## Slide 2
How to Read This Deck
Every metric here is labeled by evidence source, not asserted as fact.
VERIFIED
Pulled directly from metrics.json, STA reports, or counted from RTL/testbench source in the project archive.
CLAIMED — UNVERIFIABLE
Stated in the prior report, but no build log, bitstream, or measurement artifact exists in this archive to confirm it.
FLAGGED
A concrete discrepancy or open issue found while cross-checking the report against the underlying tool data.
RISC-V Dual-Core SoC — Verified Status Review
2

## Slide 3
Executive Summary
A working dual-core RV32I SoC with real, verified silicon-implementation data — smaller and less mature than previously reported, with open items before tape-out.
17
RTL modules
(4,294 lines)
10/10
Directed tests
passing
1,335
Std cells placed
(post-PnR, verified)
0.022 mm²
Core area
(verified, not 0.47 mm²)
Bottom line
RTL is clean and synthesizes without latches; 10/10 directed acceptance tests pass.
Actual ASIC implementation is ~20× smaller and ~400× lower power than the prior report stated.
GDS export did not complete cleanly; one fanout violation remains in the signed-off netlist.
FPGA bring-up (frequency, utilization, hardware test) has no artifacts in this archive to verify it.
RISC-V Dual-Core SoC — Verified Status Review
3

## Slide 4
System Architecture
Two RV32I cores, private caches, a coherence controller, and an AXI4-Lite fabric to shared memory and peripherals.
Core 0: rv32i_core
ALU · RegFile · Ctrl · PC · I-SRAM · D-Cache
Core 1: rv32i_core
ALU · RegFile · Ctrl · PC · I-SRAM · D-Cache
Coherence
Controller (I/S/M)
AXI4-Lite Arbiter (round-robin) → Decoder → 5 slave ranges
Shared SRAM
4 KB
MMIO Regs
UART
115200
GPIO / LED
DECERR
17 modules, 4 tiers
Cores
6 files, 1,195 ln
Memory & Cache
6 files, 1,282 ln
Bus Fabric
2 files, 390 ln
Peripherals
3 files, 898 ln
Verified: file count and line count directly counted from rtl/.
RISC-V Dual-Core SoC — Verified Status Review
4

## Slide 5
Functional Verification
Directed testbench is solid and fully accounted for. The UVM layer has a genuine scoreboard — but its “randomized” test does not randomize.
Directed Testbench — 10/10 passing
Reset (AC-9)
Single-core load/store (AC-3)
Cache hit detection (AC-2)
Cache miss + AXI fill (AC-2/3)
Cross-core coherence (AC-4/5)
Arbiter fairness (AC-8)
Multi-line, no spurious inv. (AC-2)
MMIO bypass (AC-10/7)
DECERR error (AC-11)
Counter increments
UVM Layer — 8 test classes present
Real scoreboard: golden-memory model with uvm_error on mismatch (soc_uvm_pkg.sv).
test_reset, test_cache_hit_miss, test_coherence_cross_core, test_arbiter_fairness, test_error_handling, test_mmio_counters all implemented as named UVM tests.
FLAGGED: test_randomized contains zero randomize() calls — it idles 50,000 cycles and hopes transactions accumulate. “10,000+ transactions, >85% coverage” is not backed by constrained-random stimulus.
RISC-V Dual-Core SoC — Verified Status Review
5

## Slide 6
ASIC Physical Implementation — Verified
Sourced directly from final/metrics.json and the post-PnR STA summary, sky130A / OpenLane run RUN_2026-09-09_05-42-53.
1,335
Standard cells placed
547 combinational + 196 sequential + bufs/tap
0.022 mm²
Core area
21,823 µm² (die: 27,221 µm²)
0.44 mW
Total power (post-PnR)
leakage 0.025 µW + switching 82 µW
61.6%
Utilization
std-cell placement density
+22.2 ns
Worst setup slack
worst across all 9 PVT corners
+0.18 ns
Worst hold slack
thin margin — see Risk Register
Routing closed clean: DRC errors converged 225 → 46 → 34 → 0 across four iterations; antenna violations 0.
RISC-V Dual-Core SoC — Verified Status Review
6

## Slide 7
Prior Report vs. Verified Data
FINAL_REPORT_5_COMPLETE_ARCHITECTURE.md claims figures that do not match the project's own tool outputs.
Metric
Report claimed
Verified (metrics.json / STA)
Delta
Gate count
~31,000
1,335 std cells
~20–40× over
Core area
0.47 mm²
0.022 mm²
~21× over
ASIC power
~170–200 mW
0.44 mW
~400–900× over
Timing slack
+16.8 ns
+22.2 ns (worst, post-PnR)
different stage cited
Design violations
“0, all gates passed”
1 max-fanout violation, all corners
contradicted
GDS / tape-out
“Authorized for tape-out”
GDS export step crashed; no gds/ in final output
not substantiated
RISC-V Dual-Core SoC — Verified Status Review
7

## Slide 8
Open Items & Risk Register
Concrete, evidence-based issues to close before this design is presented as tape-out ready.
High
GDS export did not complete
gds_run.log errors on a missing flow step ID; final/ has no gds/ directory. No verifiable GDSII exists despite “tape-out authorized” language.
High
Hold margin is razor-thin
Worst-case hold slack is +0.18 ns in 3 of 9 PVT corners — easily eaten by OCV/derating not modeled in this signoff.
Medium
Unresolved fanout violation
max_fanout_violation = 1 in every corner of the final signed-off netlist, despite the report's “0 violations” claim.
Medium
“Randomized” UVM test isn't random
test_randomized has no randomize() call — coverage/transaction-count claims tied to it are unverified.
Medium
FPGA results unverifiable
No bitstream, utilization report, or hardware log exists in the archive — only Makefile/XDC/flow.json configs.
Low
Module/file-count mismatch
Report states 18 modules; 17 .sv files exist under rtl/.
RISC-V Dual-Core SoC — Verified Status Review
8

## Slide 9
Recommended Next Steps
A realistic path to genuine tape-out readiness — sequenced by what blocks the next milestone.
1
Fix the GDS export step
Correct the flow config so the LibreLane/OpenLane run finishes and produces a verifiable GDSII in final/gds/.
2
Close timing risk
Re-run hold analysis with realistic OCV/derating; the current +0.18 ns margin will not survive it as-is.
3
Resolve the fanout violation
Identify and buffer the offending net; confirm 0 violations across all 9 corners before re-claiming sign-off.
4
Build real randomized verification
Add constrained-random sequences with actual randomize() calls; re-measure functional coverage honestly.
5
Capture FPGA evidence
Archive the bitstream, utilization report, and a hardware test log — currently nothing substantiates the FPGA claims.
RISC-V Dual-Core SoC — Verified Status Review
9

## Slide 10
The Core Work Is Real.
A clean, synthesizable dual-core RV32I design with a working coherence protocol
doesn't need inflated numbers to be a solid result — it needs an honest scorecard
and five concrete fixes before it's tape-out ready.
Sources: final/metrics.json · 55-openroad-stapostpnr/summary.rpt · gds_run.log · rtl/ · tb/uvm/